## Enrollment Timelines
ENROLLMENT TIMELINES
Proposed launch date |  |  |  |  | Today's Date
2022-12-31 |  |  |  |  | 2022-02-09
Audience raining window (2 weeks) |  | 17-December-2022 to 31-December-2022
Start of training |  | 17-December-2022
Capacity Planning request processed on (15th of prior month) | 15-November-2022 |  | Lesson final publish (1 day before training) | 16-December-2022
Training reviewed for bucket (week prior to 15th) | 08-November-2022 |  | Lesson edit window (3 days) | 13-December-2022 to 15-December-2022
Training enrollment intake submission window | 16-October-2022 to 07-November-2022 |  | Lesson final review complete (3 days before publish) | 12-December-2022
Enrollment FINAL DATE for submission by ID (Launch must be 100% green) | 07-November-2022 |  | Lesson review window (3 days) | 09-December-2022 to 11-December-2022
|  |  | Lesson completed for review (3 days before end of review window) | 08-December-2022
|  |  | Lesson finalization window (5 days) | 03-December-2022 to 07-December-2022
|  |  | Final screenshots and edits to lesson (must have all CSC and CX screenshots 100%) | 02-December-2022

## ID Effort Calculations
JOB DESCRIPTION | ENTER QUANTITY HERE
Existing Lesson Review | 0
Existing Lesson Updates | 0 |  | Note: These are estimates. Time estimates may vary depending on the complexity of the topic, updates, and the type of interaction agreed upon. |  |  |  |  | Example Tasks
Lesson Creation: Basic Content | 1 | [6 empty] | Create lessons | Update video | Update narration
Lesson Creation: Knowledge Checks | 0 | [6 empty] | Review lessons in curriculum | Create Video | Republish to LMS
Lesson Creation: Scenario Based Learning or Multimedia | 0 | [6 empty] | Review test | QA review by SME and ID | Check-in meetings
Create New Test/Assessment/Knowledge Check | 0 | [6 empty] | Update lessons | QA review by CSA
Update Multimedia* | 0 |  | * Audio = low complexity, Storyline animation/demo = medium complexity, Video = high complexity |  |  |  |  | Update/Create tests | Edits from QA reviews
Create New Multimedia* | 1 | [7 empty] | Final QA review
Check-in Meetings | 0
Total ID hours: | 50 | Outsourced hours: |  | 60
Task Description | Change Type | Complexity | Time Estimate (hrs.) | Outsourced | Outsourced Setup | Complexity Setup | Type Setup
Test | Lesson Creation: Basic Content | Medium | 50 | No |  | E | 7
Test 2 | Create New Multimedia* | High | 60 | Yes | 60 | F | 12

## Hour Explanation
Type | Row reference | Description | Design/Development estimates
|  |  | Low | Medium | High | Quantity Reference
|  |  | D | E | F
Existing Lesson Review | 5 | Review of content in existing lessons | 1 | 1 | 2 | 0
Existing Lesson Updates | 6 | Project does not require launch training, but new hire or specialty training will need to be updated so it remains current. | 5 | 15 | 30 | 0
Lesson Creation: Basic Content | 7 | Presentation of basic information on a single topic that is read by the learner to track that each CSA opened the lesson and acknowlegdes they recived the information. | 40 | 50 | 60 | 1
Lesson Creation: Knowledge Checks | 8 | Overview of a single topic, possibly including use case examples, and multiple choice knowlege check questions to validate CSAs know the content that was presented. These lessons can include basic screenshot questions where the learner must correctly identify a specific area of an image | 60 | 90 | 120 | 0
Lesson Creation: Scenario Based Learning or Multimedia | 9 | In addition to an overview of the topic(s) these lessons include scenerio based practice with feedback. These could involve complex branching so choices made in the lesson result in a variery of outcomes. Lesson completion can be dependent on the learner successfully navigating the scenerio. | 80 | 120 | 160 | 0
Create New Test/Assessment/Knowledge Check |  | Creation of new knowledge check. If required to be tied to business competencies or aligned with entire curriculum, it will be medium/high effort | 10 | 20 | 30 | 0
Update Multimedia* | 11 | * Audio = low complexity, Storyline animation/demo = medium complexity, Video = high complexity | 5 | 7 | 10 | 0
Create New Multimedia* | 12 | Creation of new animated video or live action video. Includes accessibility checks and QA * Audio = low complexity, Storyline animation/demo = medium complexity, Video = high complexity | 40 | 50 | 60 | 1
Check-in Meetings | 13 | Meetings with stakeholders or SMEs | 0.5 | 0.5 | 1 | 0
Publishing | 14 | Publication of new lessons, updated lessons, and tests (per lesson) | 1 | 1 | 2 | 2
QA Edits | 15 | Edits for QA Reviews from stakeholders and SMEs (per lesson) | 1 | 1 | 2 | 2
Localization Analysis | 16 | Includes efforts to determine parity of features, user/CSA experience, and process/procedures | 1 | 4 | 8 | 2
LOC/Trans PM | 17 | Includes work in ATMS and LQS | 1 | 1 | 2 | 2
Localization Development | 18 | Includes work on frontend to make lesson LOC friendly, formatting fixes, and screenshot/media updates | 4 | 12 | 30 | 2
LOC QA | 19 | QA of a lesson | 4 | 15 | 30 | 2
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43